| To: | Matthew Naud Environmental Coordinator | From: | Glen Wiczorek, PE Michael Chelminsk, PE |
| --- | --- | --- | --- |
|  | City of Ann Arbor |  | Stantec Consulting |
| File: | 2075090900 | Date: | January 23, 2009 |

Reference:	Preliminary Opinion of Probable Cost for Removal of the Argo Dam
Huron River, Ann Arbor, MI

This memo summarizes the preliminary opinion of probable costs by Stantec Consulting (Stantec) for the removal of the Argo Dam on the Huron River, Ann Arbor, Michigan.  This opinion of probable costs is based upon standard construction industry estimating techniques and Stantec’s experience from similar projects, and is intended for planning purposes for the City of Ann Arbor.  Use of this opinion of probable costs for any purpose requires understanding and acknowledgment that it is conceptual and was prepared 1) using limited, available information (i.e. aerial photographs), and 2) with a limited or preliminary level-of-effort.

Assumptions used in the preparation of this opinion of probable costs include the following:

- No contamination issues or sediment removal required;

- No issues with upstream utilities and/or infrastructure (e.g., bridge);

- The Argo Dam headpond can be dewatered prior to construction;

- A favorable regulatory climate exists for permitting in-stream and dam removal work;

- The dam abutments would remain in place so as to limit impacts to adjacent areas;

- The dam spillway and overlying gates would be removed to below the existing river bed grade;

- The dam is constructed of approximately 3,700 cubic yards of reinforced concrete with two 15-foot depth sheet pile cutoff walls/foundation driven under the dam and downstream apron;

- Access for dam removal would be from a staging area on the right (west) side of the Huron River immediately downstream (south) from the confluence of Allen Creek, and that this would necessitate construction of a temporary access road from the staging area to the dam that would cross the confluence of Allen Creek with the Huron River;

- Concrete removal may be done without containment of residual concrete material resulting from chipping/hammering of concrete during dam demolition; and

- A suitable site(s) exists for disposal of dam demolition debris within a 20-mile round-trip hauling distance.

Note that the assumed construction approach did not consider potential opportunities for reuse or disposal of concrete rubble from the dam removal in the immediate vicinity of the dam, such as disposal in the adjacent head race as part of a decommissioning of the head race.

This opinion of probable costs is based on an assumed means and methods for dam removal at this site.  The actual means and methods for removal of the Argo Dam would likely be determined by a selected construction contractor.

The opinion of probable costs for construction work as described above is approximately $1,000,000.  Professional engineering services are estimated as approximately 10 percent of construction costs ($100,000).  Costs for acquisition of necessary permits for dam removal projects can vary substantially, and have exceeded construction costs for some projects.  We have assumed that a favorable regulatory climate exists for removal of this dam, and therefore estimated that permitting costs would represent 15 percent of construction costs ($150,000).

Stakeholder engagement (e.g., preliminary public meetings) was also included here, as this process can represent an important component for building public consensus for dam removal projects.  We estimate that stakeholder engagement activities would represent 2 percent of construction costs ($20,500).

The total opinion of probable costs for complete dam removal, subject to the assumptions listed above, is approximately $1,300,000.

STANTEC CONSULTING INC.				STANTEC CONSULTING INC.

Michael Chelminski, PE					Glen Wiczorek, PE

Senior Associate, Environmental Management		Associate, Environmental

michael.chelminski@stantec.com			glen.wiczorek@stantec.com

| Description |  | Estimating Unit | Total Incl O&P |  |  | Job Quantity (units) | Estimated Cost |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Administrative |  |  |  |  |  |  |  |  |
| 01300-350-0250 | Insurance Bond | Project | 2.0% |  |  |  | See below |  |
| 01300-350-0450 | Insurance Equipment floater | Project | 1.5% |  |  |  | See below |  |
| Temporary Facilities & Controls |  |  |  |  |  |  |  |  |
| 01500-250-0550 | 6-foot Temporary Chain Link fencing | L.F. | $7.15 |  |  | 200 | $1,430 |  |
| Site Preparation |  |  |  |  |  |  |  |  |
| 02220-130-1220 | Concrete Demo | C.F. | $4.10 |  |  | 100000 | $410,000 |  |
| 02200-130-4250 | Concrete Disposal | C.Y. | $13.50 |  |  | 3704 | $50,000 |  |
| 02315-490-1255 | Hauling, 20 mi rnd trip 20 C.Y. truck | L.C.Y. | $10.20 |  |  | 2000 | $20,400 |  |
|  | x20% for traffic |  | 12.24 |  |  | 2000 | $24,480 |  |
| 02220-370-0040 | Torch Cutting (gates, bridge superstructure) | Ea. | $1.58 |  |  | 1000 | $1,580 |  |
| 02220-370-0020 | Torch Cutting (cutoff wall) | L.F. | $1.12 |  |  | 1000 | $1,120 |  |
| 02300-250-0010 | Equipment mob/demob | Ea. | $500.00 |  |  | 16 | $8,000 |  |
| 02300-2315-3300 | 300' haul, sand gravel fill | L.C.Y. | $2.33 |  |  | 2500 | $5,825 |  |
| 02315-490-1255 | Hauling, 20 mi rnd trip 20 C.Y. truck | L.C.Y. | $10.20 |  |  | 2500 | $25,500 |  |
|  | x20% for traffic |  | 12.24 |  |  | 2500 | $30,600 |  |
| 02315-210-5010 | “Select” Granular Fill | B.C.Y. | $9.65 |  |  | 2500 | $24,125 |  |
| 02315-520-0020 | Fill Placement w/ Dozer | L.C.Y. | $1.59 |  |  | 2500 | $3,975 |  |
| 02370-700-0020 | Jute Netting | S.Y. | $1.26 |  |  | 100 | $126 |  |
| 02370-700-1100 | Silt Fence | L.F. | $1.05 |  |  | 3000 | $3,150 |  |
| 02370-700-1250 | Staked haybales | L.F. | $2.75 |  |  | 3000 | $8,250 |  |
| 02510-720-3090 | 8-footx18-foot concrete pipe | L.F. | $575.00 |  |  | 36 | $20,700 |  |
|  |  |  |  |  |  | Subtotal A: | $639,261 |  |
|  | Insurance/Bonds |  |  |  |  | 2% | $12,785 |  |
|  | Insurance Equipment Floater |  |  |  |  | 1.5% | $9,589 |  |
|  |  |  |  |  |  | Subtotal B: | $22,374 |  |
|  |  |  |  |  |  | Subtotal A + B: | $661,635 |  |
|  |  |  | 10% Overhead |  |  | 10.0% | $66,163 |  |
|  |  |  |  |  |  | Subtotal C: | $66,163 |  |
|  |  |  |  |  |  | Subtotal A + B + C: | $727,798 |  |
|  |  |  |  | 10% Profit |  | 10.0% | $72,780 |  |
|  |  |  |  |  |  | Subtotal D: | $72,780 |  |
|  |  |  |  |  |  | Subtotal A+B+C+D: | $800,578 |  |
|  |  |  | Adjustment for Inflation |  |  |  |  |  |
|  |  |  | Means Manual Date: |  |  | 2005 |  |  |
|  |  |  | Assumed Construction Year: |  |  | 2010 |  |  |
|  |  | Years for Inflation Adjustment: |  |  |  | 5 |  |  |
|  |  |  | Assumed Annual Inflation: |  |  | 5% |  |  |
|  |  |  |  |  |  | Inflation Multiplier: | 1.28 |  |
|  |  |  |  | Total with Inflation Adjustment: |  |  | $1,024,740 |  |
|  |  |  | Professional Services |  |  |  |  |  |
|  |  |  |  | Service |  | % Cost |  |  |
|  |  |  |  | Engineering: |  | 10% | $102,474 |  |
|  |  |  | Permitting |  |  | 15% | $153,711 |  |
|  |  |  | Stakeholder Engagement: |  |  | 2% | $20,495 |  |
|  |  |  |  | Total of Professional Services: |  |  | $276,680 |  |
|  |  |  |  |  |  | Grand Total: | $1,301,400 |  |