## Recovery Agreement Action Plan
Item Number | Results and Determinations from Assessment | Desired Outcome | Statutory Measurement |  | Target Accomplishment Date | Actual Accomplishment Date | Remedies | Comments /Accomplishments
|  |  | Baseline Data and PHAS Score as of 9/30/2011 | Required PHAS Score
AREA: GOVERNANCE
GO01 | The Board of Commissioners does not provide the required governance over the Ypsilanti Housing Commission's (YHC) programs, finances and the Executive Director. | To have a full qualified and informed Board of Commissioners (BOC) to include one Resident Commissioner. |  |  | 2012-11-01
GO01b |  | The BOC attends the PHARS Board Training provided by HUD staff. |  |  | 1/1/2013 .
GO01c |  | The BOC be evaluated by the Appointing Official on an Annual basis to determine the need to continue with the appointee or a need to have him/her removed from the Board. |  |  | On-going/Annually
GO02 | YHC does not have a permanent Executive Director. | BOC hire a full time qualified Executive Director (ED) to run the Low Rent Public Program (LRPH). |  |  | 1/1/2013 or before
GO02a |  | BOC to create and have posted publicly an announcement for its Executive Director search. BOC must consult with HUD for guidance and technical assistance through the hiring process. The BOC will make available an opportunity for two Council Members to attend (but not participate in) the interview process. |  |  | Immediately upon execution of the Recovery Agreement
GO02b |  | BOC to create a new Job Description and Responsibilities Form for ED. |  |  | 11/1/2012 .
GO02c |  | BOC create a Contract for ED and execute upon hire. |  |  | 12/1/2012 .
GO02d |  | BOC create a Self Evaluation and Annual Appraisal for ED. |  |  | 2013-06-01
G003 | The Appointing Official, City Council, BOC and YHC lacks cohesiveness in partnership. | BOC via YHC provides monthly reports to the Appointing Official who shares report with City Council. The report must include but not limited; progress of hiring a permanent ED, status on all open audits, status on all open and the closure of all findings, status on repayment due to HUD and/or YHC's Low Rent/(transferred)Section 8 program, and status of YHC's financial position, etc. |  |  | Ongoing beginning 10/01/12 (To be re-evaluated after 1 year)
GO03a |  | Invitation be extended to Appointing Official and City Council or designee to attend any and/or all trainings held by or with the BOC. |  |  | At least two weeks prior to scheduled training
GO03b |  | Conduct quarterly "confabs" between YHC, Appointing Official, City Council and HUD (if requested). |  |  | On-going beginning 01/01/13 (To be re-evaluated after 1 year)
GO04 |  | YHC provides a yearly report to the Appointing Official and City no more than one month after the close of its Fiscal Year. |  |  | On-going beginning 07/01/13
AREA: FINANCE
FI01 | YHC is transferring its Home Choice Voucher program. | BOC and new ED evaluates its current staff level and wages and make any needed changes to remain financially stable on LRPH side. |  |  | 3/1/2013 .
FI02 | YHC received a zero score out of 11 in its Months Expendable Net Assets Ratio (MENAR). | Increase MENAR score to three within one year. | 0 | 11 | 2013-10-01
FI03 | The YHC lacks understanding of the Financial aspects of the agency (e.g. used LRPH funds to support its non-LRPH mixed finanance project). | ED and others with financial management responsibilities are trained on the financial operations of the YHC, including oversight of the fee accountant. | 2 | 25
FI03a |  | All policies and procedures regarding fianance be re-evaluated and revised as necessary. ED to increase all internal controls and implement new Board approved polocies and procedures. |  |  | 3/1/2013 . .
FI04 | The YHC does not have quality in its fee accountant. | To re-evaluate and procure for a fee accountant immediately upon execution of the Recovery Agreement. A fee accountant must be under an executed contract by date specified in Target Accomplishment Date column. |  |  | 2013-01-01
AREA: PROCUREMENT GOVERNANCE AND EXECUTION
PGE01 | YHC's Procurement files are incomplete and provides no documenation, therefore is not in compliance with YHC Procurement Policy. | Complete all procurement files according to its procurement policy. |  |  | 2013-03-01
PGE01a |  | BOC, ED and appropriate staff responsible must attend procurement training. |  |  | 2013-07-01
AREA: PROGRAMMATIC GOVERNANCE AND EXECUTION
PRGE01 | YHC Occupancy Rate is below the National and Field Office's goal. | YHC must decrease and maintain its vacancy rate below 3%. | 91.9% | 93% National 97% State Goal | 2013-01-01
PRGE01b |  | Decrease and maintain a unit turnaround rate of 21 days or less. |  |  | 2013-02-01
PRGE02 | YHC's Capital program has severe deficiencies as evidence by the lack of documentation and very poor record keeping. | ED, BOC and appropritate staff be trained on the Capital Fund Program and its procedures. |  |  | 2013-07-01
PRGE03 | YHC have outstanding HUD reviews and audit findings. | Close all HUD Reviews and findings. Close all future reviews and findings by deadline given. |  |  | 2013-07-01
9/18/12 Ypsilanti City Council
Housing Authority shall submit monthly progress reports to the Field Office using this Action Plan as the reporting template commencing 11/01/12 and every month thereafter until the Recovery Agreement is terminated."